## Requirements
Not using these columns at this point as this is a new project and the process and sub-processes have not been defined yet. Later in the project, as the system design takes shape and the teams are formed, these would be filled in. For an existing system, we would fill these in as we will most likely know which process will be impacted by which requirements and which teams will work on each requirement. This would apply to an established organization with already existing systems and teams formed around those systems. | [10 empty] | Columns to be used later throughout the project as we get organized and begin defining the use cases and dev objects to be created to satisfy the requirement
Team | Process | Sub-Process | Functional Requirement ID | Functional Requirement Description | Requirement Source | Requirement Type | Requirement Priority | Notes / Assumptions | Reviewer / Approver (Business Sponsor) | Requirement Status | Use Case ID | Development Object ID | Test Case ID
|  |  | FR-100 | Capture daily CBOT prices for corn and soy | Project Overview | Functional | Critical | An interface will need to be developed. This is a 'must have'. Our preferred interface would be a web service call | TBD | Open
|  |  | FR-101 | Capture fat market prices | Project Overview | Functional | High | Fat prices are not as volatile as corn and soy, so this interface may turn into a screen that an be used to manually input the prices | Joyce | Open
| W |  | TR-100 | Connections must be laid to the mill | Project Overview | Technical | Critical | The mill only has phone lines connecting it to the outside world at this point. The system will require a higher speed connection. Absolute 'must have' to make the system work. | Rick | Open
|  |  | TR-101 | New hardware will be required at the mill | Project Overview | Technical | Medium | The PCs at the mill will suffice, but for optimum performance and reliability, this equipment should be replaced | Rick | Open
|  |  | FR-102 | Ingredients must be received into the system inventory | Project Overview | Functional | High | To best manage the feed schedule, all feed ingredients will be booked into inventory when they are received. | Joyce | Open
|  |  | TR-102 | Investigate scanners for inventory receiving | Interview with Rick | Technical | Medium | Rick would like the receving process to be streamlined and is open to the idea of investigating handheld scanners to expedite this process | Rick | Open
|  |  | FR-103 | Interface inventory system to milling system | Interview with Rick | Functional | Medium | for maintaining accurate inventory, all ingredients that will be used in the daily production schedule will be automatically relieved from inventory | John | Open
|  |  | FR-104 | Inventory will be held on a moving average basis | Interview with Rick | Functional | High | The system must support the calculation of the moving average cost for all ingredients | Joyce | Open
|  |  | FR-105 | Scaling system will be tied into the inventory system | Project Overview | Functional | Low | The desire is to manage the bulk products by increasing inventory based on data from the scaling system. (This is a low priority because the current manual process is working just fine, but Rick would like to reduce the errors caused by human input) | Rick | Open
|  |  | FR-106 | Contracts must be captured in the system | Project Overview | Functional | Critical | As Rick writes out the contracts, he will enter them into the system, including scanning of physical documents for electronic storage, etc. (This requirement will need to be further investigated in order to turn the 'etc' in the previous sentence into real requirements | Rick | Open
|  |  | FR-107 | Create a projection algorithm | Project Overview | Functional | Critical | The algorithm will be developed along with Rick but will include CBOT and Fat market pricing as well as other components. (More investigation will be necessary to break this 'epic' into smaller user stories | Rick

## Values
Data Values
Team | Status | Effort | Requirement Type | Requirement Priority | Requirement Status | Blueprint Status | Mitigation Approach | New / Modify / Use As Is | RICEFW Type | Build Cycle
SOM-Sales Order Mgmt / Pricing | 1. Not Started | Very High | Functional | Critical | Open | Fit | Configuration | New | Report | Cycle 1
TPM-Trade | 2. In Process | High | Technical | High | Approved | Gap | RICEFW | Modify | Interface | Cycle 2
PROC-SC Execution-Procurement | 3. Drafted | Medium | Reporting | Medium | Rejected | Not in Scope | Change Impact | Use As Is | Conversion | Cycle 3
LOG-SC Execution-Logistics | 4. Ready for Peer Review | Low | Security | Low |  | Deferred |  |  | Extension
OPS-SC Execution-Operations | 5. Ready for Approval | N/A | Compliance | [5 empty] | Form
IBP-Integrated Business Planning | 6. Complete | Out of scope | Data | [5 empty] | Workflow
RD-Research & Dev | 7. Issues |  | Quality of Service
CON-Finance-Controlling | 8. N/A |  | Integrated
ACC-Finance-Accounting |  |  | Data Conversion
MD-Master Data
HR-Human Resources
BW-BW Reporting
INF-Infrastructure
SEC-Security
SALE-Sales
To be confirmed
Note on K2: Build Cycle can be used if multiple cycles of configuration / development and unit test will be utilized during the Realization Build phase. (Not multiple implementations).