## Register and Analysis
Risk Register and Assessment
Risk Identification and Probability | [7 empty] | Risk Impact Quantification |  |  | Risk Response |  |  | Additional / Optional Fields
| Not using these two columns since this is the first draft of the Risk Register. Until we have a bit more definition around the project - release schedule and team organization - we would only be guessing at what to put in these columns at this point. | [10 empty] | Note that I took some liberties with this column. Usually this would always contain a date and the descriptive text I used in some cells would be part of a Notes column. |  | Not using these columns for this initial draft. These columns will be updated throughout the project as we get more information about each risk, resolve a risk.
ID | Release | Project Team | Status | Title | Description | Risk Type | Probability (A) | Impact (B) | Risk Rating (A * B) | Impact Description | Mitigation | Due Date | Assigned To | Identified by | Identified Date | Closed Date | Comments/Notes | Modified By | Last Modified Date | Modification Description
R1 |  |  | (2) Open | Some staff are not aware of the project | The staff have different levels of awareness and supportiveness when it comes to the project. | Project | 2 | 3 | High | Unless the staff is brought into the loop quickly, this could create issues with gathering requirements and make the implementation much more difficult | We need to develop a communication plan to address each user and group to bring them from their current standing to at least a supportive role in the project. We will also need a plan quickly to make sure we include the correct people in the requirements gathering. (Rick will help us with this.) | Follow up weekly as the proejct begins; will ontinue to monitor throughout and may lengthen between follow ups if our mitigation plan seems to be working | PM
R2 |  |  | (2) Open | Requirements are not well known | We have only a very high level understanding of the requirements at this point. We will need to spend a lot of time with Rick to nail down the vision and scope of the project | Project | 4 | 4 | Max | Without clear requirements, there is no way to measure success of the project. | We will propose an inception phase with a 2 week iteration to spend time with Rick and his staff to develop a solid list of requirements. | 2018-10-26 | Analyst
R3 |  |  | (2) Open | Scale system integration | The team has little experience with this interface technology | Project | 4 | 2 | High | If this risk cannot be overcome, some of the requirements will have to be scheduled for later releases or dropped | As part of the first iteration, the team will investigate the interface and technology and run a small proof-of-concept | 2018-11-02 | Architect
R4 |  |  | (2) Open | Overall lack of team knowledge about the business process | The team is new to this business and will need to come up to speed quickly to make the project successful | Project | 3 | 3 | Max | This will most likely cause the project schedule to be longer than whatever the initial plan is and the quality of the product will suffer | The team will crosstrain with the business prior to the project beginning | 2018-11-02 | PM
R5 |  |  | (2) Open | Unhappy staff | The senior member of the team is at risk of quitting | Project | 2 | 4 | High | If this risk actually occurs, then the impact would be much the same as the risk above. The lack of experience left on the team would definitely have an impact on the schedule and quality of the product. | We will select the next strongest team member to shadow the unhappy employee to try to close this gap | 2018-10-25 | PM | Note: This risk would almost definitely not be in the public Risk Register. A PM always has a private register for this sort of risk.
Probability (A)
1 - less than 30%
2 - between 30-60%
3 - between 60-90%
4 - greater than 90%
Impact (B)
1 - Low Impact
2 - Medium Impact
3 - High Impact
4 - Very High Impact
Risk Rating (A*B)
Low (1,2) - Very slight chance that it will occur and if it does occur, it will not have a great impact on the project.
Normal (3,4) - Normal risk that should be addressed before it becomes High or Max.
High (6,8) - Risk should be addressed before it becomes a threat to the project.
Max (9,12,16) - Risk will occur and pose as a threat to the project if action items are not executed immediately.
Note on A12: ID: Insert the unique tracking number that stays with each risk during the risk lifecycle.
Note on D12: Status: Select the current status of the risk from the drop down list.
Note on E12: Title: Insert an abbreviated title to identify risk.
Note on F12: Description: Insert a description of the risk.
Note on H12: Probability: Select the probability of this risk occurring from the drop down list. 1 (Low)- less than 30% 2 (Med)- between 30-60% 3 (High)- between 60-90% 4 (Max)- greater than 90% The ranges for L/M/H/Mx will vary by project.
Note on I12: Impact: Select the impact that this risk would have on the project if it occurred from the drop down list. 1 (Low)- impact is less than $50k 2 (Med)- impact is between $50k and $100k 3 (High)- impact is greater than $100k and $250K 4 (Max)- impact greater than $250K The ranges for L/M/H/Mx dollar amounts will vary by project.
Note on J12: Risk Rating: Insert the overall risk level calculated from the multiplication of Prob & Impact.
Note on K12: Impact Description: Insert a description of the impact of this risk occurring.
Note on L12: Mitigation: Describe the response steps taken to mitigate the risk.
Note on M12: Due Date: Insert the deadline for the risk to be resolved/ closed.
Note on N12: Assigned To: Defines who is responsible for executing mitigations and managing the risk.
Note on O12: Identified By: Insert the person who identified the risk.
Note on P12: Identified Date: Insert the date the risk was identified.
Note on Q12: Closed Date: Insert the date the risk was closed or deferred.
Note on R12: Comments/Notes: Insert any comments about any activity related to the risk.
Note on S12: Modified By: Insert the person that last edited the risk.
Note on T12: Last Modified Date: Insert the date that the risk was last edited.
Note on U12: Modification Description: Insert a description of the modifications to the risk (include all modifications).

## Values
Status | Probability | Impact | Project Team Members | Type | Release | Team
(1) New | 1 | 1 | PM | Product | Update Values tab | Update Values tab
(2) Open | 2 | 2 | Analyst | Project
(3) Deferred | 3 | 3 | Architect | Deployment
(4) Closed | 4 | 4 |  | Performance