## Register and Analysis
Risk Register and Assessment
Risk Identification and Probability | [7 empty] | Risk Impact Quantification |  |  | Risk Response |  |  | Additional / Optional Fields
ID | Release | Project Team | Status | Title | Description | Risk Type | Probability (A) | Impact (B) | Risk Rating (A * B) | Impact Description | Mitigation | Due Date | Assigned To | Identified by | Identified Date | Closed Date | Comments/Notes | Modified By | Last Modified Date | Modification Description
1 |  |  |  |  | Customer Order Management | Project | 2 | 3 | High
2
Probability (A)
1 - less than 30%
2 - between 30-60%
3 - between 60-90%
4 - greater than 90%
Impact (B)
1 - Low Impact
2 - Medium Impact
3 - High Impact
4 - Very High Impact
Risk Rating (A*B)
Low (1,2) - Very slight chance that it will occur and if it does occur, it will not have a great impact on the project.
Normal (3,4) - Normal risk that should be addressed before it becomes High or Max.
High (6,8) - Risk should be addressed before it becomes a threat to the project.
Max (9,12,16) - Risk will occur and pose as a threat to the project if action items are not executed immediately.
Note on A12: ID: Insert the unique tracking number that stays with each risk during the risk lifecycle.
Note on D12: Status: Select the current status of the risk from the drop down list.
Note on E12: Title: Insert an abbreviated title to identify risk.
Note on F12: Description: Insert a description of the risk.
Note on H12: Probability: Select the probability of this risk occurring from the drop down list. 1 (Low)- less than 30% 2 (Med)- between 30-60% 3 (High)- between 60-90% 4 (Max)- greater than 90% The ranges for L/M/H/Mx will vary by project.
Note on I12: Impact: Select the impact that this risk would have on the project if it occurred from the drop down list. 1 (Low)- impact is less than $50k 2 (Med)- impact is between $50k and $100k 3 (High)- impact is greater than $100k and $250K 4 (Max)- impact greater than $250K The ranges for L/M/H/Mx dollar amounts will vary by project.
Note on J12: Risk Rating: Insert the overall risk level calculated from the multiplication of Prob & Impact.
Note on K12: Impact Description: Insert a description of the impact of this risk occurring.
Note on L12: Mitigation: Describe the response steps taken to mitigate the risk.
Note on M12: Due Date: Insert the deadline for the risk to be resolved/ closed.
Note on N12: Assigned To: Defines who is responsible for executing mitigations and managing the risk.
Note on O12: Identified By: Insert the person who identified the risk.
Note on P12: Identified Date: Insert the date the risk was identified.
Note on Q12: Closed Date: Insert the date the risk was closed or deferred.
Note on R12: Comments/Notes: Insert any comments about any activity related to the risk.
Note on S12: Modified By: Insert the person that last edited the risk.
Note on T12: Last Modified Date: Insert the date that the risk was last edited.
Note on U12: Modification Description: Insert a description of the modifications to the risk (include all modifications).

## Values
Status | Probability | Impact | Project Team Members | Type | Release | Team
(1) New | 1 | 1 | Update Values tab | Product | Update Values tab | Update Values tab
(2) Open | 2 | 2 |  | Project
(3) Deferred | 3 | 3 |  | Deployment
(4) Closed | 4 | 4 |  | Performance